## DATA
序号 S/N | SDRL Code | Package No. (RFQ no.) | Package Name | Originator Name | Project No. | Org. Code | Sector Code | Function Code | Doc Type | Doc Sub Type | Short Code | Sheet No. | Doc. No | Document Title | Client Doc No. | Contract No | Chain Code | Entity Type | Entity Sub Type | Client Submission（Y/N） | Class Submission | Planned Manhour | Validity Status | Plan Date |  |  |  |  | Forecast Date |  |  |  |  | Discipline | Prepare Person | Review Person | Approve Person | Qc Person | Doc Person
[15 empty] | Client Doc No. | [6 empty] | Planned Manhour
[24 empty] | Start | DED-IFR | DED-IFA | DED-IFC | DED-IAB | Start | DED-IFR | DED-IFA | DED-IFC | DED-IAB
1 | N.A. | N.A. | N.A. | Oceanstar Marine & Offshore Pte. Ltd. | OS | P320 | DD | ET | LA | 02 | 00001 | - | OS-P320-DD-ET-LA-02-00001 | Antena Layout | - | 1 - IFR-IFA-IFC-IAB | 4 | DWG | ISO | N | N | 100 | N.A. | 2024-01-15 | 2024-03-15 | 2024-04-15 |  |  | 2024-01-15 | 2024-03-15 | 2024-04-15 |  |  | EIT | test@11.com | test@11.com | test@11.com | test@11.com | test@11.com

## 数据填写说明
序号 S/N | Package No. (RFQ no.) | Package Name | Project No. | Yinson Doc. No. | Document Title | Document Chain | Discipline | BudgetManHour
1 | RFQ (C) 007 | Marine Engineering | 2101 | 2101-OSMO-44-P-XA-00001_01 | UFD - Bilge System | 1 - IFR-IFD-IFC-IAB
填写说明： 1.黄色背景为必填项
ST | Y | INIT
PI | N | UPDATE
PR | N.A | VOID
OU
ARSA
ME
HVAC
EIT
NA
OTHER

## SETTING
Settings
39ff0b55bb5a44bef4247f62bdfea990
Sheet Name | Entity Type | Entity Class | Entity Builder | Entity Repository | Header Rows | Max Parents | columnSettingSheet | Entity Table | parent EL fomular | keyNo El Fomular
DATA | Drawing | com.ose.tasks.entity.drawing.Drawing | com.ose.tasks.domain.model.service.drawing.builder.DrawingEntityBuilder | com.ose.tasks.domain.model.repository.drawing.DrawingRepository | 2 | 1 | COLUMN_SETTING | saint_whale_tasks.drawing | ${#function +"_"+ #docType} | ${#dwgNo}
DATA | WBSEntityEntryDate | com.ose.tasks.entity.wbs.entry.WBSEntityEntryDate | com.ose.tasks.domain.model.service.plan.builder.WBSEntityEntryDateBuilder |  | 2 | 0 | COLUMN_SETTING_DATE | saint_whale_tasks.wbs_entry_entity_date |  | ${#dwgNo}

## COLUMN_SETTING
Settings |  |  | 注：CODE列表示关键字段，必须要有的字段
Column Name | Column Index | isTableColumn | Description | Is Displayed | CODE | remark
sdrlCode | 1 |  | SDRL Code
packageNo | 2
packageName | 3
originatorName | 4
orgCode | 6
function | 8 | N | Function Code |  | FUNCTION
docType | 9 |  | Doc Type |  | TYPE
docSubType | 10 |  | Doc Sub Type |  | SUB_TYPE
shortCode | 11
sheetNo | 12
dwgNo | 13
documentTitle | 14
clientDocNo | 15
contractCode | 16
chainCode | 17 |  | Chain Code |  | CHAIN
reviewChain | 17
entityType | 18 |  | entity Type |  | ENTITY_TYPE
entitySubType | 19 |  | Entity Sub Type |  | ENTITY_SUB_TYPE
clientSubmission | 20
classSubmission | 21
planHours | 22
discipline | 34 |  | Discipline Code |  | Discipline
displayName | 13
no | 13
preparePerson | 35
reviewPerson | 36
approvePerson | 37
qcPerson | 38
docPerson | 39

## COLUMN_SETTING_DATE
Settings |  | 注：AO3表示固定单元格；39，40，41...表示序列单元格，
Column Name | Column Index | isTableColumn | Description | Is Displayed | CODE | isKeyColumn
processNo | 25,26,27,28 | N |  |  | processId
entityNo | 13 | N | Entity Id, dwgNo |  | entityId
planStartDate | 24,25,26,27
planEndDate | 25,26,27,28
forecastStartDate | 29,30,31,32,
forecastEndDate | 30,31,32,33
planHours | 22