## DATA
序号 S/N | SDRL Code | Package No. (RFQ no.) | Package Name | Originator Name | Project No. | Org. Code | Sector Code | Function Code | Doc Type | Doc Sub Type | Short Code | Sheet No. | Doc. No | Document Title | Document Chain | Chain Code | Progress Stage (INIT时非必填) | Rev.No. (INIT时非必填) | Upload Date | Outgoing Transmittal | Incoming Transmittal | Reply Date | Reply Status | DCR_No | DCR Outgoing Date | DCR Reply Date | DCR Request | DCR Status | For Client Submission（Y/N） | Client Doc. Rev | Client Doc. No | Validity Status | Surveillance Type | IDC Check | IDC Sponsor | IDC Date（xxxx/xx/xx） | Plan Date | [5 empty] | Forecast Date | [5 empty] | Discipline | BudgetManHour | Status
[37 empty] | Start | IFR | IFD | IFC | IFI | IAB | Start | IFR | IFD | IFC | IFI | IAB
1 | A01 | RFQ (C) 007 | Marine Engineering | Oceanstar Marine & Offshore Pte. Ltd. | 2101 | OSMO |  | 00 | A | LA | 00001 | - | 2101-OSMO-00-A-LA-00001 | Supplier Master Document Register (SMDR) | 3 - IFR-IAB | Chain3 | [12 empty] | Y | N.A | N.A | N.A | N.A | Y | Daijun | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-07-17 | ST | 2

## 数据填写说明
序号 S/N | Package No. (RFQ no.) | Package Name | Project No. | Yinson Doc. No. | Document Title | Document Chain | Discipline | BudgetManHour
1 | RFQ (C) 007 | Marine Engineering | 2101 | 2101-OSMO-44-P-XA-00001_01 | UFD - Bilge System | 1 - IFR-IFD-IFC-IAB
填写说明： 1.黄色背景为必填项
ST | Y | INIT
PI | N | UPDATE
PR | N.A | VOID
OU
ARSA
ME
HVAC
EIT
NA
OTHER

## Settings
Code | Desc | Column
SECTOR | Sector Code | 7
FUNCTION | Function Code | 8
TYPE | Doc Type | 9
SUB_TYPE | Doc Sub Type | 10
CHAIN | Chain Code | 16
Discipline | Discipline Code | 49